## Sheet1
Sprint Number | Ideal Tracking (Sprints) | Actual Tracking (Sprints) | Comments
1 | 51 | 51
2 | 37 | 41 | Dylan: Some user stories were not completed in sprint 1. Incomplete user stories were moved to sprint 2 with clients approval.
3 | 21 | 21 | Dylan: All user stories schedualed for completion in sprint 2 were completed.
4 | 11 | 13 | Dylan: 2 user stories were not completed in sprint 3. These user stories were moved to sprint 4 with clients approval.
5 | 0 | 0 | Dylan: All user stories have been completed.